## Danh gia ban dau
STT | Ma | Nhom viec | Dau viec chi tiet | Muc uu tien | Danh gia hien tai | Trang thai
|  | 1. Sua he thong bang mau (CSS Variables) |  |  | Roi — ten bien khong khop gia tri
1 | 1.1 |  | Doi ten bien CSS cho dung ngu nghia (--teal: #000 -> --primary-dark...) | Cao |  | Chua bat dau
2 | 1.2 |  | Loai bo hardcode #b2e8e8 (teal cu), thay bang bien CSS thong nhat | Cao |  | Chua bat dau
3 | 1.3 |  | Xay dung palette nhat quan xoay quanh gradient CTA #ff7a3d -> #f04438 | Cao |  | Chua bat dau
|  | 2. Cai thien Typography |  |  | Don dieu — mot font cho moi thu
4 | 2.1 |  | Them display font cho heading (VD: Shippori Mincho) | Trung bình |  | Chua bat dau
5 | 2.2 |  | Them clamp()/max() cho heading dung don vi vw | Trung bình |  | Chua bat dau
|  | 3. Lam lai Hero Section |  |  | Yeu — phu thuoc hoan toan vao anh
6 | 3.1 |  | Chuyen noi dung hero tu anh PNG sang HTML text that | Cao |  | Chua bat dau
7 | 3.2 |  | Giu hinh anh lam background, them fallback | Cao |  | Chua bat dau
8 | 3.3 |  | Loai bo hack margin-top: -75px | Trung bình |  | Chua bat dau
|  | 4. Cai thien Service Cards |  |  | Harsh — den + vang neon choi mat
9 | 4.1 |  | Thay phoi mau service cards: bo den + vang neon #FFFF59 | Trung bình |  | Chua bat dau
10 | 4.2 |  | Loai bo inline style hack margin-left: -12px | Thấp |  | Chua bat dau
|  | 5. Chuyen bang so sanh sang HTML |  |  | Kem — dung anh JPEG
11 | 5.1 |  | Tao HTML <table> thay the cho newtable.jpeg | Cao |  | Chua bat dau
12 | 5.2 |  | Dam bao bang responsive tren mobile | Cao |  | Chua bat dau
13 | 5.3 |  | Them alt text / caption cho accessibility | Trung bình |  | Chua bat dau
|  | 6. Don dep Code Quality |  |  | Kem — duplicate CSS, tracking la, HTML loi
14 | 6.1 |  | Xoa thuoc tinh bis_skin_checked (201 lan) | Thấp |  | Chua bat dau
15 | 6.2 |  | Gop CSS duplicate: phase-header/2/3 -> modifier class | Trung bình |  | Chua bat dau
16 | 6.3 |  | Gop CSS duplicate: phase-badge/2/3 -> modifier class | Trung bình |  | Chua bat dau
17 | 6.4 |  | Loai bo 46 lan !important, sua specificity dung cach | Trung bình |  | Chua bat dau
18 | 6.5 |  | Sua HTML loi: thieu </p> o FAQ section (~dong 719) | Thấp |  | Chua bat dau
19 | 6.6 |  | Xoa tracking scripts cua ecnomikata.com (~dong 1078-1104) | Cao |  | Chua bat dau
|  | 7. Sua Responsive / Breakpoints |  |  | Trung binh — breakpoint chong cheo
20 | 7.1 |  | Hop nhat cac block @media bi duplicate | Trung bình |  | Chua bat dau
21 | 7.2 |  | Giam va chuan hoa he thong breakpoint | Trung bình |  | Chua bat dau
|  | 8. Cai thien Accessibility |  |  | Yeu — hero/bang bang anh, thieu alt text
22 | 8.1 |  | Them alt text mo ta dung cho tat ca anh | Trung bình |  | Chua bat dau
23 | 8.2 |  | Chuyen CTA header tu anh arrow2.png sang text/SVG | Trung bình |  | Chua bat dau
24 | 8.3 |  | Chuyen FAQ sang <details>/<summary> hoac ARIA accordion | Trung bình |  | Chua bat dau
25 | 8.4 |  | Them skip navigation link o dau trang | Thấp |  | Chua bat dau
TONG KET |  | 8 nhom viec chinh | 22 dau viec chi tiet

## SOLID Refactoring
STT | Ma | Phase | Nguyen tac SOLID | Dau viec | Chi tiet / Vi tri code | Muc uu tien | Trang thai
Phase 0: Don dep & Bao mat
1 | 0.1 | Phase 0 | BẢO MẬT | Xoa tracking scripts ecnomikata.com | index.html:1078-1104 — Yahoo, FB Pixel (x2), Clarity, HubSpot, Ferret-One, Mieruca, Bing Ads, Twitter pixel, Google Ads (x2), homeup-iframe, Channel chat, uniweb-script. Giu GTM-T4NNLRW neu cua WA+CRAFT. | Khẩn cấp | Chua bat dau
2 | 0.2 | Phase 0 | BẢO MẬT | Xoa thuoc tinh bis_skin_checked="1" | index.html — 201 lan xuat hien. Do BitDefender browser extension inject. | Cao | Chua bat dau
3 | 0.3 | Phase 0 | BẢO MẬT | Xoa file duplicate root vs public | index.html = public/index.html (giong het), style.css = public/style.css (giong het). Xoa ban root. | Cao | Chua bat dau
4 | 0.4 | Phase 0 | BẢO MẬT | Xoa file proxy.ts | proxy.ts:1-14 — hack redirect / -> /index.html, khong can khi dung Next.js App Router. | Cao | Chua bat dau
Phase 1: Kien truc Next.js (Nen tang)
5 | 1.1 | Phase 1 | S+D | Chuyen index.html -> Next.js App Router components | Tao cau truc: app/ (layout, page, api/contact), components/ (layout/, sections/, ui/, common/), lib/ (api.ts, constants.ts), styles/ (tokens.css, *.module.css). | Khẩn cấp | Chua bat dau
6 | 1.2 | Phase 1 | D | Cau hinh app/layout.tsx dung chuan | Self-host Google Fonts qua next/font/google (Noto Sans JP). Metadata day du (OGP, viewport, lang='ja'). Bo CDN link. | Cao | Chua bat dau
7 | 1.3 | Phase 1 | I | Thay Bootstrap bang CSS native | index.html:8-9 load ~200KB Bootstrap chi dung grid (col-md-4, row) va 4-5 icons footer (bi-*). Thay grid -> CSS Grid/Flexbox. Icons -> SVG inline. | Cao | Chua bat dau
8 | 1.4 | Phase 1 | S+D | Tao app/api/contact/route.ts | Chuyen logic form submit tu inline JS (index.html:969-1026) sang Next.js API Route. Them validation Zod + rate limiting. | Cao | Chua bat dau
Phase 2: S — Single Responsibility
9 | 2.1 | Phase 2 | S | Tach moi section thanh component rieng | 9 sections: Hero, Problems, WhyChooseUs, Services, Comparison, Benefits, HowItWorks, FAQ, FinalCTA. Moi section = 1 .tsx + 1 .module.css. | Cao | Chua bat dau
10 | 2.2 | Phase 2 | S | Tach ContactForm dung chung | Form copy-paste 2 lan: index.html:798-831 (mobile) + index.html:876-912 (sidebar). Tao 1 ContactForm.tsx nhan props layout. | Cao | Chua bat dau
11 | 2.3 | Phase 2 | S | Tach JavaScript thanh modules/hooks | FAQ toggle -> FaqItem.tsx (useState). Form submit -> Server Action. Scroll animation -> useIntersectionObserver.ts. Modal -> PrivacyModal.tsx. | Cao | Chua bat dau
12 | 2.4 | Phase 2 | S | Tach data ra khoi markup -> constants.ts | 6 problem cards, 5 service cards, 6 step cards, 6 FAQ items hardcode trong HTML. Chuyen thanh array trong lib/constants.ts. | Trung bình | Chua bat dau
Phase 3: O — Open/Closed
13 | 3.1 | Phase 3 | O | Gop phase-header/2/3 -> PhaseCard component | style.css:276-278 — 3 class gan giong het. Tao <PhaseCard number='01' variant='light'¦'dark' />. | Cao | Chua bat dau
14 | 3.2 | Phase 3 | O | Gop phase-badge/2/3 vao PhaseCard | style.css:279-281 — 3 class badge copy-paste. Nam trong PhaseCard, style theo variant prop. | Cao | Chua bat dau
15 | 3.3 | Phase 3 | O | Tao SectionHeader component tai su dung | Moi section copy-paste block: section-en-bg + section-heading + section-desc. Tao <SectionHeader bgText label title desc />. | Cao | Chua bat dau
16 | 3.4 | Phase 3 | O | Loai bo 46 lan !important | style.css — 46 lan !important. Dung CSS Modules (scoped). Xoa block override cuoi file (style.css:1110-1126). | Trung bình | Chua bat dau
17 | 3.5 | Phase 3 | O | Xoa inline style hacks | index.html:450 style='margin-left:-12px'. index.html:229,295,359 style='width:100%'. Chuyen vao CSS module. | Thấp | Chua bat dau
Phase 4: L — Liskov Substitution
18 | 4.1 | Phase 4 | L | Dat lai ten CSS variables dung ngu nghia | style.css:16-29 — --teal:#000 (den!), --red:#000 (den!), --yellow:#666 (xam!). Doi thanh --color-primary, --color-surface, --color-accent... | Cao | Chua bat dau
19 | 4.2 | Phase 4 | L | Loai bo 13 lan hardcode #b2e8e8 | style.css — 13 lan hardcode mau teal cu. Thay bang var(--color-border). | Cao | Chua bat dau
20 | 4.3 | Phase 4 | L | Thong nhat mau #FFFF59 (vang neon) | Service cards (style.css:318), why-us (420), step CTA (465). Quyet dinh giu/thay -> dat var(--color-highlight). | Trung bình | Chua bat dau
21 | 4.4 | Phase 4 | L | Thong nhat font-size bang clamp() | Heading 3.2vw, 2.4vw khong upper bound (style.css:240,243). Chuan hoa: clamp(28px, 3.2vw, 42px). | Trung bình | Chua bat dau
Phase 5: I — Interface Segregation
22 | 5.1 | Phase 5 | I | Xoa ~380 dong CSS khong dung (dead code) | .fail-card (~50), .voice-card (~30), .section-case (~80), .nationwide-* (~40), .marquee-* (~40), .phase-header-ec (~10), .company-page* (~130). Tong 24% CSS la dead code. | Cao | Chua bat dau
23 | 5.2 | Phase 5 | I | Hop nhat duplicate @media blocks | 4 block @media(max-width:768px): style.css:947, 1274, 1289, 1547. 2 block @media(max-width:1100px): 1141, 1391. | Trung bình | Chua bat dau
24 | 5.3 | Phase 5 | I | Chuyen bang so sanh JPEG -> HTML table | index.html:493 dung newtable.jpeg — khong responsive, khong accessible, kem retina. Tao ComparisonTable.tsx. | Cao | Chua bat dau
25 | 5.4 | Phase 5 | I | Chuyen Hero anh -> HTML text | index.html:55 dung newbgan1.png chua text — Google khong index, screen reader khong doc. Tao HeroSection.tsx. | Cao | Chua bat dau
26 | 5.5 | Phase 5 | I | Xoa ~80 dong HTML comment out | index.html:167-177 (CTA cu), 581/597/611/626 (step buttons), 743-775 (3 FAQ items). | Thấp | Chua bat dau
27 | 5.6 | Phase 5 | I | CTA header: anh arrow2.png -> text/SVG | index.html:43 — <button> chua anh arrow2.png, chi co aria-label. Thay bang text that hoac SVG + text. | Trung bình | Chua bat dau
Phase 6: D — Dependency Inversion
28 | 6.1 | Phase 6 | D | Self-host fonts qua next/font | Thay CDN link fonts.googleapis.com (index.html:7) bang: import { Noto_Sans_JP } from 'next/font/google'. Next.js tu optimize. | Cao | Chua bat dau
29 | 6.2 | Phase 6 | D | Abstract form submission -> lib/api.ts | index.html:996 hardcode fetch('/api/contact'). Tao lib/api.ts: export async function submitContactForm(data). | Trung bình | Chua bat dau
30 | 6.3 | Phase 6 | D | Component nhan data qua props, khong hardcode | Section components nhan data qua props. Data dinh nghia trong lib/constants.ts voi TypeScript interfaces. | Trung bình | Chua bat dau
31 | 6.4 | Phase 6 | D | Image optimization qua next/image | Toan bo <img src='assets/...'> -> <Image>. Tu dong lazy load, responsive sizes, WebP, priority cho above-the-fold. | Cao | Chua bat dau
32 | 6.5 | Phase 6 | D | To chuc lai thu muc assets | Assets lon xon giua assets/ va img/. Chuyen vao: public/images/ (hero/, icons/, illustrations/, logos/). | Thấp | Chua bat dau
33 | 6.6 | Phase 6 | D | Pin dependency versions trong package.json | package.json dung 'latest' cho next, react, react-dom — nguy hiem. Pin: next ^15.3.0, react ^19.1.0. | Cao | Chua bat dau
TONG KET |  | 7 phases |  | 33 dau viec chi tiet
Khan cap: 2 ¦ Cao: 16 ¦ Trung binh: 10 ¦ Thap: 5
|  | Phase |  | So viec | Muc tieu
|  | Phase 0 |  | 4 | Xoa tracking la, code rac, files duplicate
|  | Phase 1 |  | 4 | Chuyen static HTML -> Next.js App Router
|  | Phase 2 (S) |  | 4 | Tach monolith -> components + modules
|  | Phase 3 (O) |  | 5 | Component tai su dung, bo copy-paste CSS
|  | Phase 4 (L) |  | 4 | Design tokens dung ngu nghia, clamp()
|  | Phase 5 (I) |  | 6 | Xoa 380 dong CSS chet, HTML thay anh
|  | Phase 6 (D) |  | 6 | Self-host, abstract API, next/image, pin versions

## Cau truc de xuat
STT | Duong dan | Mo ta
1 | app/layout.tsx | Root layout: html, body, next/font, metadata OGP
2 | app/page.tsx | Trang chinh: compose tat ca sections
3 | app/globals.css | CSS reset + design tokens (variables)
4 | app/api/contact/route.ts | API Route xu ly form submit + validation Zod
5 | components/layout/Header.tsx | Header: logo, email, CTA button
6 | components/layout/Header.module.css | CSS scoped cho Header
7 | components/layout/Footer.tsx | Footer: contact info, links
8 | components/layout/Footer.module.css | CSS scoped cho Footer
9 | components/layout/SidebarForm.tsx | Sidebar form co dinh ben phai (desktop)
10 | components/layout/SidebarForm.module.css | CSS scoped cho SidebarForm
11 | components/sections/HeroSection.tsx | Hero: headline text + background image
12 | components/sections/ProblemsSection.tsx | 6 problem cards tu data
13 | components/sections/WhyChooseUsSection.tsx | 3 PhaseCards (01/02/03)
14 | components/sections/ServicesSection.tsx | 5 service cards tu data
15 | components/sections/ComparisonSection.tsx | HTML table thay the JPEG
16 | components/sections/BenefitsSection.tsx | 5 benefit cards tu data
17 | components/sections/HowItWorksSection.tsx | 6 step cards tu data
18 | components/sections/FaqSection.tsx | FAQ accordion tu data
19 | components/sections/FinalCtaSection.tsx | CTA + mobile form toggle
20 | components/ui/PhaseCard.tsx | Thay phase-header/2/3 — props: variant, number, title
21 | components/ui/ProblemCard.tsx | Card van de — props: icon, title, items[]
22 | components/ui/ServiceCard.tsx | Card dich vu — props: icon, title, text
23 | components/ui/BenefitCard.tsx | Card benefit — props: image, title, text
24 | components/ui/StepCard.tsx | Card step — props: number, image, title, text
25 | components/ui/FaqItem.tsx | Client component: Q/A toggle (useState)
26 | components/ui/ContactForm.tsx | Form dung chung — props: layout='sidebar'¦'full'
27 | components/common/SectionHeader.tsx | Dung lai cho moi section — props: bgText, label, title, desc
28 | components/common/PrivacyModal.tsx | Client component: modal privacy policy
29 | lib/api.ts | Abstract API calls: submitContactForm()
30 | lib/constants.ts | Data arrays: FAQ_ITEMS, SERVICES, STEPS, PROBLEMS, BENEFITS
31 | lib/types.ts | TypeScript interfaces: FaqItem, ServiceItem, StepItem...
32 | hooks/useIntersectionObserver.ts | Custom hook thay scroll animation inline JS
33 | styles/tokens.css | Design tokens: --color-*, --font-*, --spacing-*, --radius-*
34 | public/images/hero/ | Anh hero section
35 | public/images/icons/ | Icons (problem, service, step)
36 | public/images/illustrations/ | Minh hoa (benefit, step)
37 | public/images/logos/ | Logo WA+CRAFT